Scheduling and Pacing Planner

The Hackles Kit

Hackles · a free kit · quillsup.org · October 2026

© 2026 Competence Collective. Lesson text and teaching materials CC BY-NC 4.0. The Hackles name, logos, characters and artwork are not covered by that license: print and share them unaltered for classroom and family use; any other use needs written permission. [VERIFY with counsel]

Status: DRAFT for local review, 2026-10-05. Not legal advice. Hackles has not been reviewed, approved or endorsed by FLDOE or any state agency. It has not been evaluated in a controlled study. Every legal or statistical statement is marked [VERIFY] or [COUNSEL TO CONFIRM]; ask your own counsel before relying on it.

Two ready-made calendars for each grade band: a 12-week plan (one lesson a week) and a 36-week plan (a lesson about every three weeks, with review weeks). Both give the counselor three weeks' warning and families two weeks' notice for sensitive lessons. Adjust for your calendar, testing windows and breaks. [COUNSEL TO CONFIRM your notice period]

## How the lessons run

10 core lessons per band, 15 minutes each: Hook 2, Activity 8, Discuss 3, Takeaway and exit ticket 2.

Sensitive lessons (see the Counselor Coordination Protocol): K-2 L6 and L9; 3-5 L1 and L6; 6-8 L1, L6, L7, L8; 9-12 L5, L7, L8.

Plus lessons for grades 6 to 12 are optional extensions: 6-8 P1 to P3, 9-12 P1 to P4. P1 (trafficking) and P2 (mental health) wait until your specialist or clinician review is done. [VERIFY with the kit's Plus changelog]

The optional pre and post surveys take 10 to 15 minutes each (K-2 about 10, oral). Use only what counsel clears. [COUNSEL TO CONFIRM]

## Placement rules for sensitive lessons

1. Schedule mid-morning or earlier. Avoid the last period and the day before a break.

2. Avoid Fridays when the counselor is part-time on Fridays.

3. Allow at least two class meetings after a sensitive lesson before the next one in the same class.

4. Keep the counselor's free time on the calendar before you commit the date.

5. Do not teach one on a testing day.

## The 12-week plan (one lesson a week)

Weeks -3 to 0 are preparation. Weeks 1 to 12 are teaching weeks. "Notice" means the family pre-notice goes home; "Heads-up" means the teacher messages the counselor.

| WEEK | ACTIVITY (ALL BANDS) |
| --- | --- |
| -3 to 0 (preparation) | Week -3: staff session and counselor confirmation for any sensitive lesson in Weeks 1 to 3. Week -1: family letter 1 goes home, with the pre-notice for a sensitive Lesson 1. Week 0: teacher heads-up messages |
| 1 | Pre survey (if used). Lesson 1 |
| 2 to 10 | Lessons 2 to 10 |
| 11 | Catch-up and review. Post survey (if used) |
| 12 | Family showcase or Hackles Day. Counts to the tracker. Teacher debrief |

### Lesson placement by band

| BAND | WEEKS 1 TO 10 | SENSITIVE LESSON WEEKS | NOTICE GOES HOME |
| --- | --- | --- | --- |
| K-2 | L1 to L10 in order | L6 in week 6, L9 in week 9 | Weeks 4 and 7 |
| 3-5 | L1 to L10 in order | L1 in week 1, L6 in week 6 | Week -1 (with Letter 1) and week 4 |
| 6-8 | L1 to L10 in order | L1 in week 1, L6, L7, L8 in weeks 6 to 8 | Week -1, then weeks 4, 5 and 6 |
| 9-12 | L1 to L10 in order | L5, L7, L8 in weeks 5, 7, 8 | Weeks 3, 5 and 6 |

Weeks 6, 7 and 8 in 6-8 and weeks 7 and 8 in 9-12 put sensitive lessons back to back. If your counselor cannot support that, use the 36-week plan or insert the break week below: teach Lesson 9 or 10 (not sensitive) between them in 6-8, and put a review activity between L7 and L8 in 9-12.

### Optional Plus block for grades 6 to 12 (weeks 13 to 16)

| WEEK | 6-8 | 9-12 |
| --- | --- | --- |
| 13 | P3 Fact, Fiction or Fake | P3 Whose Goal Is It |
| 14 | P2 Scroll Science (after clinician review) | P2 Mind, Mood, and the Scroll (after review) |
| 15 | P1 Work, Pressure and Promises Online (after specialist review) | P1 Recruitment Online (after specialist review) |
| 16 | Review and post survey | P4 From Mean to Harmful, then review |

Send notices for P1 and P2 two weeks ahead. Teach P3 and P4 with a counselor heads-up only. Titles follow the slide files in kit/25_Slides. [VERIFY against your edition]

## The 36-week plan (a lesson about every three weeks)

This plan spaces lessons so that skills come back. Teachers revisit Hackles up, Pause, Check, Tell and the Help Ladder briefly in the review weeks.

| WEEKS | ACTIVITY |
| --- | --- |
| 1 to 3 | Staff session, family letter 1, pre survey, counselor planning |
| 4 | Lesson 1 |
| 5 to 6 | Two-minute daily "Hackles Up" practice (hand signal, one scenario). Notice for Lesson 2 if needed |
| 7 | Lesson 2 |
| 10 | Lesson 3 |
| 13 | Lesson 4 |
| 14 | Review week and a mid-year check of the tracker |
| 16 | Lesson 5 |
| 19 | Lesson 6 |
| 22 | Lesson 7 |
| 25 | Lesson 8 |
| 26 | Review week. Family night or Hackles Day if scheduled |
| 28 | Lesson 9 |
| 31 | Lesson 10 |
| 32 to 34 | Optional Plus lessons (grades 6 to 12) or repeat the best-liked lessons |
| 35 | Post survey, family showcase |
| 36 | Counts to the tracker. Teacher debrief. Plan next August's refresh |

### Notice and counselor dates for the 36-week plan

| SENSITIVE LESSON (BY LESSON NUMBER) | LESSON WEEK | COUNSELOR CONFIRMATION | FAMILY NOTICE |
| --- | --- | --- | --- |
| K-2 L6 | 19 | week 16 | week 17 |
| K-2 L9 | 28 | week 25 | week 26 |
| 3-5 L1 | 4 | week 1 | week 2 (send with letter 1) |
| 3-5 L6 | 19 | week 16 | week 17 |
| 6-8 L1 | 4 | week 1 | week 2 |
| 6-8 L6, L7, L8 | 19, 22, 25 | weeks 16, 19, 22 | weeks 17, 20, 23 |
| 9-12 L5 | 16 | week 13 | week 14 |
| 9-12 L7, L8 | 22, 25 | weeks 19, 22 | weeks 20, 23 |

## Grade-band tally sheet for your own use

| ITEM | YOUR DATE |
| --- | --- |
| Staff session |  |
| Family letter 1 |  |
| Pre survey |  |
| First lesson |  |
| First sensitive lesson, notice date, counselor date |  |
| Mid-year tracker check |  |
| Post survey |  |
| Family event |  |
| Counts due |  |

## Fitting the plan to your setting

| SETTING | SUGGESTION |
| --- | --- |
| Elementary classroom | Use the 12-week plan during morning meeting or a rotating specials slot |
| Middle school advisory | The 12-week plan fits an advisory block. Rotate which adult teaches so that each lesson has a counselor available |
| High school | Use health, ELA, CS or an advisory block. Choose the 36-week plan if the school cannot give 12 straight weeks |
| School library | Run each lesson as a 15-minute read-aloud or station within library time, with the classroom teacher present |
| After-school or youth program | Use the 12-week plan with the same adult each week. The program names who plays the counselor role |
| College orientation or first-year course | Use the 9-12 lessons selectively, with a campus counseling referral list. Do not reuse minors' materials without review. [VERIFY with your campus] |
| Summer program | Compress to two lessons a week for five weeks. Keep notice and counselor timing |

## Common problems

| PROBLEM | FIX |
| --- | --- |
| A holiday knocks out a lesson week | Move the whole sequence one week. Do not skip a sensitive lesson's notice date |
| Counselor is out on the planned day | Move the lesson. Never run a sensitive lesson without backup |
| A disclosure happens in week 5 | Follow the flowchart. Pause the next sensitive lesson if the counselor needs the time |
| Families ask for earlier notice | Send it. A longer notice period costs nothing |
| A class falls behind | Drop the optional hook of a non-sensitive lesson before cutting an activity. Never cut the Tell step |