Hackles Mentors · Semester Calendar

The Hackles Kit

A free kit by Competence Collective · competencecollective.org · October 2026

(c) 2026 Competence Collective. Lesson text and teaching materials CC BY-NC 4.0. The Hackles name, logos, characters and artwork are not covered by that license: print and share them unaltered for classroom and family use; any other use needs written permission. [VERIFY with counsel]

A sixteen-week plan for a fall or spring semester, built for a community college: commuter students, evening classes and short windows. Adjust to your academic calendar [LOCAL]. Schools' calendars also matter: avoid their testing windows and breaks.

TO VERIFY

Status: DRAFT. Dates are examples. Safer Internet Day (February) and National Cybersecurity Awareness Month (October) are natural anchors for events [VERIFY dates].

## Calendar

| WEEKS | PHASE | TASKS | OWNER |
| --- | --- | --- | --- |
| Before week 1 | Prepare | Documents reviewed by counsel and HR; insurance confirmed; school agreements signed; coordinator and advisor named; budget approved [COUNSEL/HR TO CONFIRM] | Advisor, coordinator |
| 1 to 3 | Recruit | Club visits, classroom announcements, info sessions (one daytime, one evening), social posts (no photos of children) | Coordinator, club leaders |
| 2 to 4 | Apply and interview | Applications, interviews, references; consent for background checks | Coordinator, advisor |
| 3 to 5 | Screen | Background checks, host school clearances | HR, coordinator |
| 4 | Training session A | Four-hour training, daytime option | Trainer, counselor |
| 5 | Training session B | Four-hour training, evening or weekend option | Trainer, counselor |
| 6 | Placement | Assign mentors to events and Station Leads; brief schools with the roster | Coordinator |
| 7 | Rehearsal | Station practice, equipment check, event run-through | Station Leads |
| 8 | Event 1 (pilot or shadow) | First school visit. New mentors shadow a Station Lead | Coordinator, advisor |
| 9 | Debrief 1 | Mentor debrief; incident review; fix the plan | Coordinator, advisor |
| 10 to 12 | Events 2 to 4 | School and library visits; one evening family event if a school asks | All |
| 12 | Check-in | Advisor and coordinator review of safety, hours and feedback | Advisor |
| 13 | Event 5 or on-campus Hackles Day | A larger event, if schools come to campus (see transport checklist) | All |
| 14 | Reflection | Mentors write reflections; hours logged | Mentors |
| 15 | Recognition | Certificates, badges, thank-you notes to schools | Coordinator |
| 16 | Close | Impact tracker finalised (aggregate counts only); report to the dean; plan next term | Coordinator, advisor |

## A typical event day (3 hours, mornings)

| TIME | TASK |
| --- | --- |
| 7:45 | Mentors arrive; sign in; brief with Station Lead |
| 8:15 | Meet the school contact; visitor badges |
| 8:30 | Stations open with the teacher leading |
| 11:15 | Close; thank the teacher |
| 11:30 | Debrief; end-of-event check-in forms; clean up |

## Evening and weekend options

Evening training (two 2-hour sessions) in weeks 4 and 5.

Saturday morning events with a library or community group.

Evening family nights with a school (adults and children together), where a school or library staff member leads.

Remote tasks for commuters: art for passports, poster design, card cutting, impact tracker support, writing the thank-you notes.

## Planning checklist (each event)

☐ School agreement current

☐ Mentor roster cleared and confirmed

☐ Station Leads assigned and briefed

☐ Ratios met

☐ Rooms, routes and accessibility checked

☐ Materials printed and counted

☐ Incident forms and emergency contact sheet

☐ Coordinator and advisor reachable

☐ Weather and contingency plan

☐ Teacher feedback form ready (no student data)

Hackles has not been evaluated in a controlled study.