Implementation in 30 Days

The Hackles Kit

A free kit by Competence Collective · competencecollective.org · October 2026

© 2026 Competence Collective. Lesson text and teaching materials CC BY-NC 4.0. The Hackles name, logos, characters and artwork are not covered by that license: print and share them unaltered for classroom and family use; any other use needs written permission. [VERIFY with counsel]

Status: DRAFT for local review, 2026-10-05. Not legal advice. Hackles has not been reviewed, approved or endorsed by FLDOE or any state agency. It has not been evaluated in a controlled study. Every legal or statistical statement is marked [VERIFY] or [COUNSEL TO CONFIRM]; ask your own counsel before relying on it.

A week-by-week playbook for a small school, library or youth organization (up to about 300 students, one or two grade bands, a part-time counselor). It assumes you want to teach your first lesson about 30 days from today, with the safeguards in place. If your district needs a formal materials review, board action or counsel sign-off, those steps may take longer than 30 days. Do them before Day 22. [COUNSEL TO CONFIRM]

## Before day 1 (the 20-minute decision)

Read Start Here for Administrators.

Decide whether you have the people: a Hackles lead (any teacher, librarian or counselor), a counselor or counselor stand-in who agrees to be on call, and one administrator who owns the decision.

Pick a first-lesson date about 4 weeks out, in a mid-morning slot, not before a break.

## Week 1 (days 1 to 7): decide, check and plan

| DAY | TASK | OWNER | DONE |
| --- | --- | --- | --- |
| 1 | Name the Hackles lead and the counselor contact. Book 30 minutes for the two of them and the administrator | Administrator | [ ] |
| 1 to 2 | Read the Procurement Brief, Security and Privacy Questionnaire and Data-Flow Statement. Fill the Procurement Brief approvals table | Business office or tech lead | [ ] |
| 2 to 3 | Send counsel the package: Start Here, Model Policy, Parent Letter Set, Counselor Coordination Protocol, the Assessment Pack surveys (if you plan to use them) and your state's page in the State Atlas. Ask for answers on state mandate, notice and opt-out, survey consent, reporting route and deadline | Administrator | [ ] |
| 3 | Counselor reads the sensitive-lesson list and the Disclosure and Incident Guide. Marks any lesson to hold back | Counselor | [ ] |
| 4 | IT picks a hosting option (print only, school server, local copy) and downloads the kit. Verify checksums | Tech lead | [ ] |
| 5 | Choose grade bands and classes. Fill the Classes sheet in the tracker | Hackles lead | [ ] |
| 6 to 7 | Write the local reporting route (agency, phone, deadline, backup) and fill the Crisis flowchart blanks | Administrator, counselor | [ ] |

Gate at the end of week 1: counsel has answered or given a date; the reporting route is written; the counselor is on board. If any of those is missing, stop and fix it before week 2.

## Week 2 (days 8 to 14): approve, schedule and prepare people

| DAY | TASK | OWNER | DONE |
| --- | --- | --- | --- |
| 8 | Put the decision on the board or cabinet agenda if required (Board Memo). Otherwise record an administrator decision | Administrator | [ ] |
| 8 to 9 | Choose the pacing plan (12-week or 36-week) and fill dates. Put sensitive lessons on the calendar with counselor and notice dates | Hackles lead | [ ] |
| 9 | Edit and approve the parent letters (general letter and the first sensitive pre-notice) | Administrator | [ ] |
| 10 | Send the Staff Memo. Book the staff session for week 3 | Hackles lead | [ ] |
| 10 to 12 | Print the Teacher Guide, the First 10 Minutes flowchart, student books and handouts. Use the copy shop specification if needed | Office | [ ] |
| 12 | Decide the survey plan. Use surveys only if counsel cleared them. Prepare paper copies | Hackles lead | [ ] |
| 13 to 14 | Set up an "ask the counselor" box or note process. Prepare the quiet space | Counselor | [ ] |

## Week 3 (days 15 to 21): train and tell families

| DAY | TASK | OWNER | DONE |
| --- | --- | --- | --- |
| 15 | Send family letter 1 (general introduction), with the contact for questions and a preview option | Teachers | [ ] |
| 16 to 17 | Staff session (60 to 90 minutes): the habit, a sample lesson, the sensitive-lesson process, disclosure practice, local reporting route, opt-outs | Hackles lead, counselor | [ ] |
| 18 | Teachers read their band's Teacher Guide and the first three lessons | Teachers | [ ] |
| 19 | Counselor confirms availability for the first sensitive lesson. Heads-up messages go out for it | Teachers, counselor | [ ] |
| 20 | Send the pre-notice for the first sensitive lesson if it is within the next three weeks | Teachers | [ ] |
| 21 | Run the pre survey (if used). Enter totals in the tracker | Teachers | [ ] |

## Week 4 (days 22 to 30): launch

| DAY | TASK | OWNER | DONE |
| --- | --- | --- | --- |
| 22 | Dry run: one teacher reads Lesson 1 aloud to the Hackles lead. Check slides and printouts | Hackles lead | [ ] |
| 23 to 24 | Last checks: reporting card in every binder, counselor schedule, opt-out slips ready, alternate activities ready | Administrator | [ ] |
| 25 | Principal visits a classroom for Lesson 1 or sends a short note of thanks | Administrator | [ ] |
| 26 to 28 | Teach Lesson 1 in each class. Tick the tracker | Teachers | [ ] |
| 28 | Quick huddle (15 minutes): what worked, what to fix, any questions from families | Hackles lead | [ ] |
| 29 | Send a short follow-up to families with a take-home card | Teachers | [ ] |
| 30 | Check the Checks sheet and Dashboard. Plan next month. Put the August refresh on the calendar | Hackles lead | [ ] |

## What each role does in the 30 days (summary)

| ROLE | HOURS OVER 30 DAYS (ESTIMATE) |
| --- | --- |
| Administrator | 4 to 6: decision, counsel contact, letters, visit |
| Hackles lead | 10 to 14: planning, tracker, training, printing |
| Counselor | 4 to 6: review, training, availability |
| Teacher | 4 to 5: training, reading, first lesson, notices |
| IT | 2 to 3: hosting, checksums, device test |
| Office | 2 to 4: printing and copying |

These are planning estimates, not measured times. [VERIFY with your own pilot]

## Risks and quick fixes

| RISK | FIX |
| --- | --- |
| Counsel needs longer than a week | Start with a non-sensitive lesson such as K-2 Lesson 2 (Secret Passwords) or 6-8 Lesson 2 (Account Defense) while you wait. Hold sensitive lessons for later. [COUNSEL TO CONFIRM that this is acceptable] |
| No counselor available | Do not teach sensitive lessons. Teach the others |
| A grade band has no counselor coverage | Teach only the non-sensitive lessons in that band |
| Families object | Offer a preview and the alternate. Do not argue |
| A teacher is nervous about disclosure | Put them with a pair for the first lesson, and rehearse the First 10 Minutes script in the staff session |
| Printing falls behind | Project the slides and use the teacher guide; print student pages later |
| A number or link looks wrong | Do not use it. Tell the Hackles lead. The kit has many [VERIFY] flags and a known error rate |

## Success after 30 days (what to look for)

Lesson 1 delivered in each class, with counts in the tracker.

Every teacher has the reporting card.

No sensitive lesson was taught without counselor heads-up and family notice.

Families know whom to ask.

The Checks sheet shows no red flags.

Do not look for "safer children" in the first 30 days. Look for a working process.